## Gantt Chart
BRIGHTTV · VIEWERSHIP ANALYTICS PROJECT
Customer Value Management · 10-Day Sprint · 20-Min Presentation Deliverable
| Task / Deliverable | Owner | Status | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | % Done
| PHASE 1 · Data Preparation |  |  | D1 | [9 empty] | Day 1
| Convert UTC → SAST (UTC+2) | Analyst | In Progress | [10 empty] | 100%
| Data profiling & quality check | Analyst | In Progress | [10 empty] | 100%
| Session-level data model | Analyst | In Progress | [10 empty] | 100%
| PHASE 2 · Exploratory Analysis |  |  |  | D2 | [8 empty] | Days 2–5
| User & usage trends | Analyst | Planned | [10 empty] | 0%
| Consumption drivers | Analyst | Planned | [10 empty] | 0%
| Low-consumption day analysis | Analyst | Planned | [10 empty] | 0%
| Supplementary data sourcing | Researcher | Planned | [10 empty] | 0%
| PHASE 3 · Strategy & Recommendations | [7 empty] | D6 |  |  |  |  | Days 6–8
| Content recommendations | Strategist | Planned | [10 empty] | 0%
| User-base growth initiatives | Strategist | Planned | [10 empty] | 0%
| KPI framework & metrics | Lead | Planned | [10 empty] | 0%
| PHASE 4 · Presentation Delivery | [10 empty] | D9 |  | Days 9–10
| Slide deck build | Analyst | Planned | [10 empty] | 0%
| Rehearsal & polish | Lead | Planned | [10 empty] | 0%
| ★ PRESENTATION DELIVERY | All | Milestone | [9 empty] | ◆ | —
LEGEND
Phase 1 · Data Preparation (Day 1)
Phase 2 · Exploratory Analysis (Days 2–5)
Phase 3 · Strategy & Recommendations (Days 6–8)
Phase 4 · Presentation Delivery (Days 9–10)
| ◆ | Milestone
In Progress
Planned